## Sprint 1
Daycare Management System
Product Backlog - Sprint 1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Week 1 | Week 2 | Week 3 | Week 4 | Sprint Review |  | Sprint Goal
As a / an website visitor (parent) I want to register myself so that I can see the most important content at a glance and quickly understand the site navigation | 1) Create the parent registration view within the presentation layer | Kevin | Open | 3 | 0 | 0 | 0 | 0 | 0 | Our goal is by the end of this sprint we have two fully functional websites that call a single SQL Database through one shared business layer.
| 2) Code the business layer in order to register a parent within the database | Steve | Open | 5 | - | - | - | - | -
| 3) Create the "Parents" table within the database | Mehrnaz | Open | 2 | - | - | - | - | -
| 4) Test the registration process once complete | Nick | Open | 3 | - | - | - | - | -
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | 1) Create the Login View within the Presentation Layer | Kevin | Open | 5 | - | - | - | - | -
| 2) Code the business layer to validate and send down to model layer and hit the database | Steve | Open | 4 | - | - | - | - | -
| 3) Create database validation for info sent back Consider: encryption of all user pws | Mehrnaz | Open | 3 | - | - | - | - | -
| 4) Change the security of the page to allow full site access | Andrew | Open | 2 | - | - | - | - | -
| 5) Ensure login process has a loading and start page. | Nick | Open | 1 | - | - | - | - | -
As a / an website visitor, I want to be able to register a child to the company and view all information regarding the child. | 1) Create the child registration page within the presentation layer | Kevin | Open | 5 | - | - | - | - | -
| 2) Code the business layer to validate and send down to model layer and hit the database | Steve | Open | 4 | - | - | - | - | -
| 3) Add "Child" tables within the database | Mehrnaz | Open | 3 | - | - | - | - | -
| 5) Ensure register process has a loading and start page. | Nick | Open | 2 | - | - | - | - | -
As a / an employee, I want to view a home page so that I can see the most important content at a glance, and quickly understand the site navigation | 1) Create the employee registration view within the solution | Kevin | Open | 5 | - | - | - | - | -
| 2) Code the business layer in order to register a employee within the database | Steve | Open | 4 | - | - | - | - | -
| 3) Create the "Employee" table within the database | Mehrnaz | Open | 3 | - | - | - | - | -
| 4) Test the registration process once complete | Nick | Open | 2 | - | - | - | - | -
As a / an employee, I want to be able to log in to the site and view all information regarding the clients of our company | 1) Create the Login View within the Presentation Layer | Kevin | Open | 5 | - | - | - | - | -
| 2) Code the business layer to validate and send down to model layer and hit the database | Steve | Open | 4 | - | - | - | - | -
| 3) Create database validation for info sent back Consider: encryption of all user pws | Mehrnaz | Open | 3 | - | - | - | - | -
| 4) Change the security of the page to allow full site access | Nick | Open | 2 | - | - | - | - | -
| 5) Ensure login process has a loading and start page. | Andrew | Open | 2 | - | - | - | - | -
As a / an employee, I want to be able to view all information regarding the registered children in order to manage the clientele. | 1) Create a view to display children information | Kevin | Open | 5 | 3 | - | - | - | -
| 2) Code the Business layer methods to pull children information from the database | Steve | Open | 4 | 2 | - | - | - | -
| Total | Nick | - | 10 | 0 | 0 | 0 | 0 | 0
| Total | Steve | - | 25 | 2 | 0 | 0 | 0 | 0
| Total | Kevin | - | 28
| Total | Mehrnaz | - | 14
| Grand Total | ALL | - | 81 | 5 | 0 | 0 | 0 | 0