## Sprint 1
Daycare Management System
Product Backlog - Sprint 1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Week 1 | Week 2 | Week 3 | Week 4 | Sprint Review |  | Sprint Goal
As a / an website visitor (parent) I want to register myself so that I can see the most important content at a glance and quickly understand the site navigation | Upload to GitHub | Stave |  | 0.5 | 0 | 0 | 0 | 0 | 0 | Our goal is by the end of this sprint we have two fully functional websites that call a single SQL Database through one shared business layer.
Original Estimate: 21 | Create first Solution | Stave |  | 1 | - | - | - | - | -
| Database Design | Mehrnaz |  | 3 | - | - | - | - | -
| Create and Test database within Source Control | Mehrnaz |  | 3
| UML Diagrams for Business Logic | All |  | 3
| Presentation Layer Design | Kevin / Nick |  | 1
| Create the default page for the site | Kevin |  | 1
| 1) Create the parent registration view within the presentation layer | Kevin | Open | 3
| 2) Code the business layer in order to register a parent within the database | Steve | Open | 5
| 3) Create the "Parents" table within the database | Mehrnaz | Open | 3
| 4) Test the registration process once complete | Nick | Open | 3
[5 empty] | - | - | - | - | -
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | 1) Create the Log in pop up within the Presentation Layer | Kevin | Open | 2 | - | - | - | - | -
Estimated: 13
| 2) Code the business layer to validate and send down to model layer and hit the database | Steve | Open | 3 | - | - | - | - | -
| 3) Create database validation for info sent back Consider: encryption of all user pws | Mehrnaz | Open | 3 | - | - | - | - | -
| 4) Change the security of the page to allow full site access | Nick | Open | 2 | - | - | - | - | -
| 5) Ensure login process has a loading and start page. | Nick | Open | 2 | - | - | - | - | -
As a / an website visitor, I want to be able to register a child to the company. | 1) Create the child registration page within the presentation layer | Kevin | Open | 2 | - | - | - | - | -
Estimated: 5 | 2) Code the business layer to validate and send down to model layer and hit the database | Steve | Open | 3 | - | - | - | - | -
Actual: 10 | 3) Add "Child" tables within the database | Mehrnaz | Open | 3 | - | - | - | - | -
| 5) Test completed task | Nick | Open | 2 | - | - | - | - | -
As a / an website visitor, I want to be able to view a registered child and view all information. | 1) Create the child view page within the presentation layer | Kevin | Open | 2
Estimate: 5 | 2) Code the business layer to validate and send down to model layer and hit the database | Steve | Open | 2
Actua Estimate: 7 | 3) Code the return stored procedures to pull children | Mehrnaz | Open | 1
| 5) Testing | Nick | Open | 2
As a / an employee, I want to view a home page so that I can see the most important content at a glance, and quickly understand the site navigation | 3) Create the "Employee" table within the database | Mehrnaz | Open | 1 | - | - | - | - | -
| 1) Create roles within the employees | Mehrnaz | Open | 0.5
| 3) Create a default page that will allow employees to log in | Kevin |  | 1
| 2) Create a maintenance page for Admin levels | Kevin |  | 2
| 1) Create the employee registration view within the maintenance page | Kevin | Open | 2
| 2) Code the business layer in order to register a employee within the database | Steve | Open | 3 | - | - | - | - | -
| 4) Test the registration process once complete | Nick | Open | 2 | - | - | - | - | -
As a / an employee, I want to be able to log in to the site and view all information regarding the clients of our company | Create the information page: Parents and Children | Kevin | Open | 3 | - | - | - | - | -
| 2) Code the business layer to pull parents then pull children based on parent | Steve | Open | 2 | - | - | - | - | -
| 3) Create SPROCS to return information on parents and children | Mehrnaz | Open | 2 | - | - | - | - | -
| 5) testing | Andrew | Open | 1 | - | - | - | - | -
As a / an employee, I want to be able to view all information regarding the registered children in order to manage the clientele. | 1) Create a view to search all children information | Kevin | Open | 2 | 3 | - | - | - | -
| 2) Code the Business layer methods to pull children information from the database | Steve | Open | 2 | 2 | - | - | - | -
| 3) Code the Sprocs to pull all children |  |  | 1
| 4) testing |  |  | 1
| Total | Nick | - | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total | Steve | - | 14 | 2 | 0 | 0 | 0 | 0
| Total | Kevin | - | 11.5
| Total | Mehrnaz | - | 12
| Grand Total | ALL | - | 79 | 5 | 0 | 0 | 0 | 0

## Product Backlog
Product Backlog
User Story | Story points | Priority | Status
As a / an website visitor (parent) I want to register myself so that I can see the most important content at a glance and quickly understand the site navigation | 21 | High | Not Started | Open
In Progress
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | 13 | High |  | Testing
Finished Testing
As a / an website visitor, I want to be able to register a child to the company and view all information regarding the child. | 8 | High |  | In Review
Closed
As a / an employee, I want to view a home page so that I can see the most important content at a glance, and quickly understand the site navigation | 5 | High |  | Abadoned
As a / an employee, I want to be able to log in to the site and view all information regarding the clients of our company | 2 | High
As a / an employee, I want to be able to view all information regarding the registered children in order to manage the clientele. | 2 | High
Parent Registers children for classes from home | 13 | Normal
Employees can leave notes for children that parents can view at home | 13 | Normal
Parents can leave notes for employees can view | 5 | Normal
Employees can send emails to a parent or a select group of parentts | 8 | Normal
Employees can generate reports that can be distributed to parents | 21 | Normal
Employees are able to check in a child | 34 | Low