## Product Backlog
Product Backlog
User Story | Story Points | Priority | Status | Status Legend
As a / an website visitor (parent) I want to register myself so that I can see the most important content at a glance and quickly understand the site navigation. | 21 | High | Not Started | 0) Not Started
1) Open
As a / an website visitor (parent) I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company. | 13 | High | Not Started | 2) In Progress
3) Testing
As a / an website visitor (parent) I want to be able to register a child to the company and view all information regarding the child. | 8 | High | Not Started | 4) Finished Testing
5) In Review
As a staff employee, I want to view a home page so that I can see the most important content at a glance, and quickly understand the site navigation. | 5 | High | Not Started | 6) Closed
7) Rejected
As a staff employee, I want to be able to log in to the site and view all information regarding the clients of our company. | 2 | High | Not Started
As a staff employee, I want to be able to view all information regarding the registered children in order to manage the clientele. | 2 | High | Not Started
As a / an website visitor (parent), I want to be able to register my children for classes from home. | 13 | Normal | Not Started
As a staff employees I want to be able to leave notes for children that parents can view at home. | 13 | Normal | Not Started
As a / an website vistor (parent) I want to be able to leave notes for employees to view. | 5 | Normal | Not Started
As a staff employees, I want to be able to send emails to a parent or a select group of parents regarding updates about their children or activities going on. | 8 | Normal | Not Started
Employees can generate reports that can be distributed to parents. | 21 | Normal | Not Started
Employees are able to check in a child. | 34 | Low | Not Started

## Sprint 1
Daycare Management System
Product Backlog - Sprint 1
Product Backlog Item | Task | Assignee | Status | Original Estimate | Week 1 | Week 2 | Week 3 | Week 4 | Sprint Review
As a / an website visitor (parent) I want to register myself so that I can see the most important content at a glance and quickly understand the site navigation | 1) Upload to GitHub | Steve | Open | 0.5 | - | - | - | - | -
Backlog Estimate: 21 | 2) Create Initial Solution | Steve | Open | 1 | - | - | - | - | -
Task Estimate: 26.5 | 3) Create Database Design | Mehrnaz | Open | 3 | - | - | - | - | -
| 4) Create and Test database within Source Control | Mehrnaz | Open | 3 | - | - | - | - | -
| 5) Create UML Diagrams for Business Logic | All | Open | 3 | - | - | - | - | -
| 6) Presentation Layer Design | Kevin | Open | 1 | - | - | - | - | -
| 7) Create the default page for the site | Kevin | Open | 1 | - | - | - | - | -
| 8) Create the parent registration view within the presentation layer | Kevin | Open | 3 | - | - | - | - | -
| 9) Code the business layer in order to register a parent within the database | Steve | Open | 5 | - | - | - | - | -
| 10) Create the "Parents" table within the database | Mehrnaz | Open | 3 | - | - | - | - | -
| 11) Test the registration process once complete | Nick | Open | 3 | - | - | - | - | -
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | 1) Create the Log in pop up within the Presentation Layer | Kevin | Open | 2 | - | - | - | - | -
Backlog Estimate 13 | 2) Code the business layer to validate and send down to model layer and hit the database | Steve | Open | 3 | - | - | - | - | -
Task Estimate: 12 | 3) Create database validation for info sent back Consider: encryption of all user passwords | Mehrnaz | Open | 3 | - | - | - | - | -
| 4) Change the security of the page to allow full site access | Nick | Open | 2 | - | - | - | - | -
| 5) Ensure login process has a loading and start page. | Nick | Open | 2 | - | - | - | - | -
As a / an website visitor, I want to be able to register a child to the company. | 1) Create the child registration page within the presentation layer | Kevin | Open | 2 | - | - | - | - | -
Backlog Estimate: 5 | 2) Code the business layer to validate and send down to model layer and hit the database | Steve | Open | 3 | - | - | - | - | -
Task Estimate: 10 | 3) Add "Child" tables within the database | Mehrnaz | Open | 3 | - | - | - | - | -
| 4) Quality Assurance Testing | Nick | Open | 2 | - | - | - | - | -
As a / an website visitor, I want to be able to view a registered child and view all information. | 1) Create the child view page within the presentation layer | Kevin | Open | 2 | - | - | - | - | -
Backlog Estimate: 5 | 2) Code the business layer to validate and send down to model layer and hit the database | Steve | Open | 2 | - | - | - | - | -
Task Estimate: 7 | 3) Code the return stored procedures to pull children | Mehrnaz | Open | 1 | - | - | - | - | -
| 4) Quality Assurance Testing | Nick | Open | 2 | - | - | - | - | -
As a / an employee, I want to view a home page so that I can see the most important content at a glance, and quickly understand the site navigation | 1) Create the "Employee" table within the database | Mehrnaz | Open | 1 | - | - | - | - | -
Backlog Estimate: 5 | 2) Create roles within the employees | Mehrnaz | Open | 0.5 | - | - | - | - | -
Task Estimate: 11.5 | 3) Create a default page that will allow employees to log in | Kevin | Open | 1 | - | - | - | - | -
| 4) Create a maintenance page for Admin levels | Kevin | Open | 2 | - | - | - | - | -
| 5) Create the employee registration view within the maintenance page | Kevin | Open | 2 | - | - | - | - | -
| 6) Code the business layer in order to register a employee within the database | Steve | Open | 3 | - | - | - | - | -
| 7) Quality Assurance Testing | Nick | Open | 2 | - | - | - | - | -
As a / an employee, I want to be able to log in to the site and view all information regarding the clients of our company | 1) Create the information page: Parents and Children | Kevin | Open | 3 | - | - | - | - | -
Backlog Estimate: 5 | 2) Code the business layer to pull parents then pull children based on parent | Steve | Open | 2 | - | - | - | - | -
Task Estimate: 8 | 3) Create SPROCS to return information on parents and children | Mehrnaz | Open | 2 | - | - | - | - | -
| 4) Quality Assurance Testing | Nick | Open | 1 | - | - | - | - | -
As a / an employee, I want to be able to view all information regarding the registered children in order to manage the clientele. | 1) Create a view to search all children information | Kevin | Open | 2 | - | - | - | - | -
Backlog Estimate: 5 | 2) Code the Business layer methods to pull children information from the database | Steve | Open | 2 | - | - | - | - | -
Task Estimate: 6 | 3) Code the Sprocs to pull all children | Mehrnaz | Open | 1 | - | - | - | - | -
| 4) Quality Assurance Testing | Nick | Open | 1 | - | - | - | - | -
| Total | Nick | - | 15 | 0 | 0 | 0 | 0 | 0
| Total | Steve | - | 21.5 | 0 | 0 | 0 | 0 | 0
| Total | Kevin | - | 21 | 0 | 0 | 0 | 0 | 0
| Total | Mehrnaz | - | 20.5 | 0 | 0 | 0 | 0 | 0
| Grand Total | ALL | - | 79 | 79 | 0 | 0 | 0 | 0
Sprint Goal
Our goal is by the end of this sprint we have two fully functional websites that call a single SQL Database through one shared business layer.